| Sample timetable Community Planning Weekend | 5-Day Event spanning weekend Local hosts, professional team Specific public sessions | Team. Organisation. Hosts. Sponsors. Invited experts. General Public. |
| --- | --- | --- |

| ## DAY 1 THURSDAY BRIEF |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 08.00 |  | ### Setting up |  | Room arrangements. Delivery of equipment and supplies. Erection of banners and signs |
|  |  |  |  |  |  | 12.00 |  | Team assembles |  | Arrangements |
|  |  |  |  |  |  | 13.00 |  | Buffet lunch |  | Welcome by hosts, sponsors etc. |
|  |  |  |  |  |  | 14.00 |  | ### Reconnaissance |  | By team of area – bus / train / plane / foot |
|  |  |  |  |  |  | 16.00 |  | Political briefings |  | By local politicians |
|  |  |  |  |  |  | 17.00 |  | Community briefings |  | By local inhabitants |
|  |  |  |  |  |  | 18.00 |  | Technical briefings |  | By planners, engineers, developers etc. |
|  |  |  |  |  |  | 19.00 |  | Team briefing |  | By chairperson on Team working process |
|  |  |  |  |  |  | 19.30 |  | Launch event (optional) |  | Public meeting and/or dinner/reception |

| ## DAY 2 FRIDAY ISSUES |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 09.00 |  | ### Team briefing and preparation |  |  |
|  |  |  |  |  |  | 10.00 |  | Setting the scene |  | Presentations by local interests |
|  |  |  |  |  |  | 13.00 |  | Topic workshop |  | Open to all, punctuated by lunch and tea breaks. Several parallel topic-based groups or one single plenary ending with plenary report back. |
|  |  |  |  |  |  | 17.00 |  | ### Team review |  | Detailed problem definition |
|  |  |  |  |  |  | 18.00 |  | Breather |  | Minute writing, reading, exercise. |
|  |  |  |  |  |  | 20.00 |  | Team dinner |  |  |

| ## DAY 3 SATURDAY SOLUTIONS |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 09.00 |  | ### Team briefing and preparation |  |  |
|  |  |  |  |  |  | 10.00 |  | Report back on Day 2 |  | By chairperson and/or Team members |
|  |  |  |  |  |  | 10.30 |  | Lessons from elsewhere |  | Presentation by team members |
|  |  |  |  |  |  | 12.00 |  | ### Design workshop |  | Open to all, punctuated by lunch and tea breaks and ending with a plenary report back in parallel groups of 10-15 |
|  |  |  |  |  |  | 17.00 |  | Team review |  | Developing central themes |
|  |  |  |  |  |  | 18.00 |  | Breather |  | Minute writing, reading, evercise. |
|  |  |  |  |  |  | 19.00 |  | Team brainstorm dinner |  | Imaginative solutions |

| ## DAY 4 SUNDAY TEAM WORKING |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 10.00 |  | ### Team preparation |  |  |
|  |  |  |  |  |  | 11.00 |  | Team editorial meeting |  | Report, presentation and production structure |
|  |  |  |  |  |  | 12.00 |  | Report presentation and production |  | Writing, editing, drawing, Powerpoint show. Review meetings as necessary. Team only. Sleep and eat as and when. |

| ## DAY 5 MONDAY PRESENTATION |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 07.00 |  | ### Printers deadline |  | Report and/or broadsheet to printers |
|  |  |  |  |  |  | All day |  | Presentation preparation |  | Image and text selection. Exhibition mounting. Hall arrangements. |
|  |  |  |  |  |  | All day |  | Clearing up |  | Tidying up, packing equipment and supplies |
|  |  |  |  |  |  | 17.30 |  | ### Press briefing |  |  |
|  |  |  |  |  |  | 19.00 |  | Public presentation |  | Powerpoint show followed by discussion and formal thanks. Distribution of report or broadsheet |
|  |  |  |  |  |  | 18.00 |  | Farewell social event |  |  |